## retrospectives
Project Type | Risk Category | Observation | Mitigation Plan | Severity
Fixed Price | Scope Creep | Unclear requirements caused frequent scope changes. | Establish a strict Change Control Board (CCB) and sign-off on a baseline requirements document in Week 1. | High
Agile | Resource Availability | Parallel allocations reduced team velocity. | Implement dedicated resource allocation; use capacity planning tools to prevent double-booking developers. | Medium
Fixed Price | Dependency Delays | Vendor dependencies delayed milestones. | Create "Interface Contracts" and mock services early so development can continue without the live vendor API. | High
Fixed Price | Infrastructure Lead Times | Client-side firewall approval took 22 days, delaying CI/CD. | Submit all IP whitelisting and firewall requests during the "Pre-Sprint" or Week 0 phase. | High
T&M | Seniority Imbalance | Team had 1 Architect; illness stalled all decisions. | Implement mandatory peer reviews and "Technical Spikes" shared across at least two senior members. | Medium
Agile | UAT Bottlenecks | Stakeholders tested at month-end instead of per sprint. | Schedule "Show & Tell" sessions every Friday with mandatory UAT sign-off for stories completed that week. | Medium
Fixed Price | API Contract Drift | External vendor changed JSON schema without notice. | Implement automated contract testing (like Pact) that runs daily against the vendor's sandbox environment. | High
Internal | Low SME Engagement | Internal experts were only allocated 2h/week. | Escalated to Project Sponsor for a minimum 25% dedicated SME allocation for the duration of Discovery. | Medium
Fixed Price | Procurement Delays | Enterprise licenses for cloud services took 15 days. | Use a "Warm-up Phase" to identify all necessary SaaS/Cloud licenses and initiate procurement in Month 1. | Medium
Agile | Scope Gold-Plating | Developers built custom auth instead of standard Cognito. | Enforce "Architecture Review" for any custom module where a standard managed service (AWS/Azure) exists. | Low
Fixed Price | Data Privacy (GDPR) | Anonymizing production data took 3 weeks longer. | Use synthetic data generation tools early; never assume production data can be used for dev/testing. | High
T&M | Time Zone Latency | 8-hour gap with PO led to 24-hour delays. | Shift daily stand-ups to a "Golden Hour" overlap and use async video updates (Loom) for requirement queries. | Low
Internal | Documentation Debt | Lack of TDD caused a 4-week onboarding delay. | Enforce "Docs as Code"; no PR is merged without updated documentation in the project Wiki. | Medium
Fixed Price | Browser Compatibility | Client mandated IE11 support mid-project. | Define a "Supported Browser Matrix" in the contract; treat new browser requirements as a Change Request. | Low
Agile | Technical Debt | Refactoring legacy schema took 3x longer. | Conduct a "Discovery Spike" to profile the database before committing to refactoring timelines. | High
Fixed Price | Security Audit Failures | Penetration testing found 5 critical vulnerabilities. | Integrate DAST/SAST (security scanning) into the CI/CD pipeline from Day 1. | High
T&M | Unmanaged Dependencies | Waiting for S3 buckets caused a 10-day idle period. | Map all cloud dependencies in a "Readiness Checklist" before developers start the implementation phase. | Medium
Agile | Estimation Optimism | Story points were consistently 50% lower than actual. | Use "Reference Stories" for estimation and apply a 1.5x buffer to the first two sprints' velocity. | Medium
Fixed Price | Mobile Fragmentation | Performance issues on low-end Android required rewrite. | Define minimum hardware specs early; perform "Smoke Tests" on real low-end devices every sprint. | Medium
Internal | Stakeholder Turnover | Original Sponsor left; new Sponsor changed vision. | Maintain a "Decision Log" signed by the steering committee to ensure continuity during leadership shifts. | Medium
Fixed Price | SSL Certificate Expiry | Expired certificates caused 4 hours of downtime. | Set up automated alerts 30 days prior to expiry and move to managed certificate services (e.g., AWS ACM). | Medium
T&M | Tooling Incompatibility | Dev used Docker; Prod only supported bare-metal. | Ensure the "Staging" environment matches "Production" architecture exactly, including the OS version. | High
Agile | Sprint Spillovers | 40% of stories moved; they were "too big." | Enforce strict "INVEST" criteria for user stories; no story should exceed 50% of total sprint capacity. | Low
Fixed Price | Third-Party Rate Limits | External API throttled migration, extending window. | Implement exponential backoff in scripts and request a temporary rate-limit increase for the migration. | Medium
Internal | Project Conflict | Key QA resources pulled to a Priority 1 emergency. | Establish a "Service Level Agreement" (SLA) for shared resources with the Internal PMO. | High
Fixed Price | Localization Complexity | Arabic RTL broke CSS layout in 60% of views. | Use "Logical Properties" in CSS and test RTL layouts during the initial UI component development. | Low
T&M | Over-reliance on Mocks | Tests passed with mocks but failed on network latency. | Implement "Chaos Engineering" or latency simulation during integration testing. | Medium
Agile | Lack of DoD | Features marked "Done" lacked unit tests. | Automate "Definition of Done" checks (e.g., 80% code coverage) within the Git pre-commit hooks. | Medium
Fixed Price | Compliance Change | New banking regulations required audit logging. | Maintain a "Regulatory Risk Register" and check for upcoming policy changes quarterly. | High
Internal | Shadow IT | Team used unapproved SaaS that was later blocked. | Provide an "Approved Tooling List"; any deviation requires prior approval from Corporate Security. | Low
Fixed Price | DB Migration Lock | Large table migrations caused production timeout. | Use online schema migration tools (e.g., gh-ost) or perform migrations during off-peak hours. | High
T&M | Unclear Success Metrics | Client expected "Speed" while team delivered "Features." | Define non-functional requirements (NFRs) like "Page Load Time" in the Project Charter. | Medium
Agile | Absence of Peer Review | Bypassing PRs led to hardcoded API key in staging. | Remove "Admin" merge rights; require at least one approval from a different developer for every PR. | High